## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want to upload PDF, TXT, and DOCX files so that the system indexes my documents. | MUST HAVE | None | Dhanushree D | 3- Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want to upload an entire folder so that all supported files are ingested at once. | MUST HAVE | US-01 | Dhanushree D | 3- Completed
Sprint 1 | Sprint 1 | US-03 | As a developer, I want documents chunked into 800-char pieces with 100-char overlap so context is not lost at boundaries. | MUST HAVE | US-01 | Dhanushree D | 3- Completed
Sprint 2 | Sprint 2 | US-04 | As a user, I want documents converted to vector embeddings using all-MiniLM-L6-v2 so that semantic search is possible. | MUST HAVE | US-03 | Dhanushree D | 3- Completed
Sprint 2 | Sprint 2 | US-05 | As a user, I want embeddings stored in ChromaDB so that fast similarity-based retrieval is available during Q&A. | MUST HAVE | US-04 | Dhanushree D | 3- Completed
Sprint 2 | Sprint 2 | US-06 | As a user, I want to upload a second document without losing the first so that multiple documents can be queried together. | MUST HAVE | US-05 | Dhanushree D | 3- Completed
Sprint 3 | Sprint 3 | US-07 | As a user, I want to ask questions in plain English and get accurate answers retrieved from my uploaded documents. | MUST HAVE | US-05 | Dhanushree D | 3- Completed
Sprint 3 | Sprint 3 | US-08 | As a user, I want source filenames shown with every answer so that I can verify the information in the original document. | MUST HAVE | US-07 | Dhanushree D | 3- Completed
Sprint 3 | Sprint 3 | US-09 | As a user, I want Corrective RAG so that if retrieved chunks are irrelevant the query is automatically rewritten and retried. | SHOULD HAVE | US-07 | Dhanushree D | 3- Completed
Sprint 4 | Sprint 4 | US-10 | As a user, I want multi-turn conversation support so that I can ask follow-up questions referencing previous answers. | MUST HAVE | US-07 | Dhanushree D | 3- Completed
Sprint 4 | Sprint 4 | US-11 | As a user, I want Home, Upload, Chat, and History pages so that navigation is clear and intuitive. | MUST HAVE | None | Dhanushree D | 3- Completed
Sprint 4 | Sprint 4 | US-12 | As a user, I want live upload progress status so that I know the system is processing and do not close the page early. | SHOULD HAVE | US-01 | Dhanushree D | 3- Completed
Sprint 5 | Sprint 5 | US-16 | As a user, I want a full chat history page so that I can review all previous questions, answers, and sources from the session. | COULD HAVE | US-10 | Dhanushree D | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 70 | 10 | 11 | 6 | 8 | 6 | 7 | 5 | 7 | 3 | 2 | 1 | 2 | 2 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Set up Reflex project structure and install all dependencies | 2026-01-05 | 2026-01-06 | G.Vinuthna | Environment Setup | 3- Completed | 2 | Day 1: 2
US-01 | T-02 | Implement PyPDFLoader for PDF file ingestion | 2026-01-06 | 2026-01-07 | G.Vinuthna | Coding | 3- Completed | 2 | Day 2: 2
US-01 | T-03 | Implement TextLoader for TXT and Docx2txtLoader for DOCX ingestion | 2026-01-07 | 2026-01-08 | G.Vinuthna | Coding | 3- Completed | 2 | Day 3: 2
US-02 | T-04 | Build DirectoryLoader with recursive glob patterns for all file types | 2026-01-08 | 2026-01-09 | G.Vinuthna | Coding | 3- Completed | 2 | Day 4: 2
US-02 | T-05 | Test directory ingestion with mixed PDF, TXT, DOCX files | 2026-01-09 | 2026-01-10 | G.Vinuthna | Testing | 3- Completed | 1 | bar: Day 1 to Day 13
US-03 | T-06 | Implement RecursiveCharacterTextSplitter chunk_size=800 overlap=100 | 2026-01-09 | 2026-01-10 | G.Vinuthna | Coding | 3- Completed | 2 | Day 6: 2
US-03 | T-07 | Test chunking boundaries and verify overlap correctness | 2026-01-10 | 2026-01-11 | G.Vinuthna | Testing | 3- Completed | 1 | bar: Day 1 to Day 13
SPRINT 2 BACKLOG
US-04 | T-08 | Integrate HuggingFace all-MiniLM-L6-v2 embedding model locally | 2026-01-12 | 2026-01-13 | G.Vinuthna | Coding | 3- Completed | 3 | Day 8: 3
US-04 | T-09 | Convert all document chunks to 384-dimensional embedding vectors | 2026-01-13 | 2026-01-14 | G.Vinuthna | Coding | 3- Completed | 2 | Day 9: 2
US-05 | T-10 | Set up ChromaDB in-memory vector store and store all embeddings | 2026-01-14 | 2026-01-15 | G.Vinuthna | Coding | 3- Completed | 2 | Day 10: 2
US-05 | T-11 | Configure retriever with k=4 using cosine similarity search | 2026-01-15 | 2026-01-16 | G.Vinuthna | Coding | 3- Completed | 1 | bar: Day 1 to Day 13
US-06 | T-12 | Implement add_documents() logic for dynamic document addition | 2026-01-15 | 2026-01-16 | G.Vinuthna | Coding | 3- Completed | 2 | Day 12: 2
US-05 | T-13 | Write ingest() pipeline combining load, split, embed, store steps | 2026-01-16 | 2026-01-17 | G.Vinuthna | Coding | 3- Completed | 2 | Day 13: 2
SPRINT 3 BACKLOG
US-07 | T-14 | Integrate Groq Llama3-8b-8192 LLM with temperature=0.2 | 2026-01-19 | 2026-01-20 | G.Vinuthna | Coding | 3- Completed | 2 | Day 1: 2
US-07 | T-15 | Build corrective_rag() function: retrieve, check relevance, rewrite, generate | 2026-01-20 | 2026-01-22 | G.Vinuthna | Coding | 3- Completed | 4 | Day 2: 4
US-08 | T-16 | Extract source filenames from document metadata for every answer | 2026-01-21 | 2026-01-22 | G.Vinuthna | Coding | 3- Completed | 2 | Day 3: 2
US-09 | T-17 | Implement check_relevance() with YES/NO LLM evaluation | 2026-01-22 | 2026-01-23 | G.Vinuthna | Coding | 3- Completed | 2 | Day 4: 2
US-09 | T-18 | Implement rewrite_query() for automatic query rewriting on failed relevance | 2026-01-22 | 2026-01-23 | G.Vinuthna | Coding | 3- Completed | 2 | Day 5: 2
US-09 | T-19 | End-to-end test Corrective RAG with ambiguous and off-topic queries | 2026-01-23 | 2026-01-24 | G.Vinuthna | Testing | 3- Completed | 1 | bar: Day 1 to Day 13
SPRINT 4 BACKLOG
US-10 | T-20 | Build ChatState with question, history, is_loading, is_uploading, ingest_done | 2026-01-26 | 2026-01-27 | G.Vinuthna | Coding | 3- Completed | 3 | Day 1: 3
US-10 | T-21 | Implement manual history injection — last 6 turns appended to every prompt | 2026-01-27 | 2026-01-28 | G.Vinuthna | Coding | 3- Completed | 2 | Day 2: 2
US-10 | T-22 | Fix Reflex reactivity — replace list.append() with new list assignment | 2026-01-27 | 2026-01-28 | G.Vinuthna | Bug Fix | 3- Completed | 1 | bar: Day 1 to Day 13
US-11 | T-23 | Build Home page with hero, feature cards, and navigation links | 2026-01-28 | 2026-01-29 | G.Vinuthna | Build | 3- Completed | 2 | Day 4: 2
US-11 | T-24 | Build Upload page with rx.upload, file chips, and process button | 2026-01-28 | 2026-01-29 | G.Vinuthna | Build | 3- Completed | 2 | Day 5: 2
US-11 | T-25 | Build Chat page with conversation bubbles, input, send button, source badges | 2026-01-29 | 2026-01-30 | G.Vinuthna | Build | 3- Completed | 3 | Day 6: 3
US-11 | T-26 | Build History page showing full session Q&A with sources | 2026-01-29 | 2026-01-30 | G.Vinuthna | Build | 3- Completed | 2 | Day 7: 2
US-12 | T-27 | Fix upload page closing bug — add is_uploading flag and yield-based status | 2026-01-30 | 2026-01-31 | G.Vinuthna | Bug Fix | 3- Completed | 2 | Day 8: 2
US-12 | T-28 | Add ingest_done flag and manual Go to Chat button after success | 2026-01-30 | 2026-01-31 | G.Vinuthna | Build | 3- Completed | 1 | bar: Day 1 to Day 13
SPRINT 5 BACKLOG
US-13 | T-29 | Add extract_chart_data() in rag.py to parse numerical data from context | 2026-02-02 | 2026-02-03 | G.Vinuthna | Coding | 3- Completed | 3 | Day 1: 3
US-13 | T-30 | Integrate Reflex chart components for bar and line charts in chat UI | 2026-02-03 | 2026-02-04 | G.Vinuthna | Build | 3- Completed | 3 | Day 2: 3
US-13 | T-31 | Test data visualization with numerical document content | 2026-02-04 | 2026-02-05 | G.Vinuthna | Testing | 3- Completed | 1 | bar: Day 1 to Day 13
US-14 | T-32 | Add detect_language() and inject language instruction into LLM prompt | 2026-02-04 | 2026-02-05 | G.Vinuthna | Coding | 3- Completed | 2 | Day 4: 2
US-14 | T-33 | Test multi-language queries — Telugu, Hindi, English documents | 2026-02-05 | 2026-02-06 | G.Vinuthna | Testing | 3- Completed | 1 | bar: Day 1 to Day 13
US-15 | T-34 | Implement reset_session() — clear vectorstore, history, documents | 2026-02-05 | 2026-02-06 | G.Vinuthna | Coding | 3- Completed | 1 | bar: Day 1 to Day 13
US-16 | T-35 | Build History page with clear history button and complete Q&A display | 2026-02-05 | 2026-02-06 | G.Vinuthna | Build | 3- Completed | 2 | Day 7: 2
US-01 | T-36 | Final integration testing — all 5 sprints end-to-end verified | 2026-02-06 | 2026-02-07 | G.Vinuthna | Testing | 3- Completed | 2 | Day 8: 2
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Set up Reflex project, installed all dependencies. Created project folder structure including backend, states, pages, components. | Dhanushree D
Sprint 1 | Day 2 | LangChain and ChromaDB version conflicts on installation | Resolved by pinning compatible package versions in requirements.txt. Successfully loaded first PDF using PyPDFLoader. | Dhanushree D
Sprint 1 | Day 3 | Difficulty choosing optimal chunk size — small size lost context, large exceeded retrieval quality | Tested chunk sizes 300, 500, 800 chars. Finalized chunk_size=800 with chunk_overlap=100 as best balance. | Dhanushree D
Sprint 1 | Day 4 | HuggingFace model slow on first run due to large download size | Model cached locally after first download. All subsequent runs load instantly from local cache. | Dhanushree D
Sprint 1 | Day 5 | DirectoryLoader glob patterns not matching files in subdirectories | Fixed glob to **/*.pdf, **/*.txt, **/*.docx. All file types in nested directories now load correctly. | Dhanushree D
Sprint 2 | Day 1 | None | Integrated all-MiniLM-L6-v2 locally. Generated 384-dim vectors for all chunks. No API key required. | Dhanushree D
Sprint 2 | Day 2 | ChromaDB vectorstore lost data between calls due to variable scoping in rag.py | Made vectorstore a global variable. Persists correctly across multiple ingest calls within one session. | Dhanushree D
Sprint 2 | Day 3 | add_documents() creating duplicate chunks when re-ingesting same file | Added file path tracking to skip already-ingested files. Dynamic addition works correctly. | Dhanushree D
Sprint 2 | Day 4 | Cosine similarity retrieving low-quality chunks for short single-word questions | Tuned retrieval, verified k=4 returns relevant long-form chunks for all tested short queries. | Dhanushree D
Sprint 2 | Day 5 | None | Sprint 2 complete. Ingest pipeline tested with 3 different PDFs. All chunks stored and retrievable. | Dhanushree D
Sprint 3 | Day 1 | Groq API key not loading from environment — KeyError on startup | Added os.environ.get() with descriptive EnvironmentError. Key now loads correctly before app starts. | Dhanushree D
Sprint 3 | Day 2 | LLM ignoring document context and answering from own training knowledge | Added explicit instruction: 'Answer based on provided context only.' Hallucination eliminated in all tests. | Dhanushree D
Sprint 5 | Day 1 | Reflex UI not updating after new answer appended to chat history | Replaced list.append() with self.history = self.history + [new_turn]. Reactivity now works correctly. | Dhanushree D
Sprint 4 | Day 2 | Upload page closing immediately after clicking Upload & Process button | Added is_uploading flag with yield-based status. Removed auto-redirect. Page stays until ingest completes.
Sprint 4 | Day 3 | ImportError: cannot import ChatTurn from states.rag_state | Removed ChatTurn from chat.py import. History stored as list[dict] — no custom dataclass needed.
Sprint 4 | Day 4 | Chat page crashing when sources list is empty for a response | Added rx.cond() check for sources.length() > 0 before rendering badges. No crash on empty sources.
Sprint 4 | Day 5 | None | Sprint 4 complete. All 4 pages working. Full upload → chat → history → reset flow tested successfully.
Sprint 5 | Day 1 | LLM returning chart data JSON in inconsistent formats | Used regex to extract JSON from response. Added try/except returning None gracefully on parse failure.
Sprint 5 | Day 2 | Language detection adding noticeable latency to every query | Made detection a lightweight single LLM call. Latency under 300ms — acceptable for current scope.
Sprint 5 | Day 3 | Reflex chart component crashing when chart_data is None | Added rx.cond(turn['chart_data'] != None, ...) guard. Charts render only when valid data present.
Sprint 5 | Day 4 | None | Final integration testing across all 5 sprint features. Data visualization and multi-language verified working.
Sprint 5 | Day 5 | None | Project complete. Code cleaned, documented. Presentation and live demo prepared. Submission ready.

## Retrospection
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 05-Jan-2026 | 17-Jan-2026 | G.Vinuthna | Write unit tests alongside code | Leaving dependency setup to last moment | Daily commit habit and progress tracking | Set up environment on Day 1. Documented all dependency versions in requirements.txt.
2 | Sprint 2 | 19-Jan-2026 | 31-Jan-2026 | G.Vinuthna | Test each pipeline stage independently before integration | Assuming code works without running retrieval quality checks | Using global variable consistently for vectorstore state | Added retrieval quality tests with sample questions before proceeding to LLM integration.
3 | Sprint 3 | 02-Feb-2026 | 14-Feb-2026 | G.Vinuthna | Add prompt constraints from the start (context-only instruction) | Relying on LLM to self-limit without explicit instructions | Corrective RAG relevance-check pattern — very effective | Added context-only instruction to all prompts. Eliminated hallucination in all tests.
4 | Sprint 4 | 16-Feb-2026 | 28-Feb-2026 | G.Vinuthna | Use is_uploading and ingest_done flags for all async operations | Using auto-redirect before async operations complete | yield-based live status updates in Reflex state methods | Fixed upload page closing bug. Replaced auto-redirect with manual Go to Chat button.
5 | Sprint 5 | 02-Mar-2026 | 14-Mar-2026 | G.Vinuthna | Add try/except around all LLM JSON parsing operations | Assuming LLM always returns consistent output format | End-to-end integration testing before declaring sprint complete | Added regex JSON parsing with fallback. Final demo tested successfully across all features.